## Prompts & Fixes
RemoEd PH — Prompts & Bug Fixes Tracker (from Cursor session)
Updated Sep 27, 2026 02:29 AM (UTC+8) ¦ Window: Sep 26, 2026 9:00 PM → now ¦ Focus: Platform prompts & stability fixes
TOTAL TASKS |  | COMPLETED |  | ONGOING |  | SCHEDULED / PENDING |  | All listed prompts in this window are Done. No open Pending items at generation time.
25 |  | 25 |  | 0 |  | 0
Task ID | Owner | Deliverables & Task Description | Phase / Window | Status | Priority | Start Date | Target Date | Notes & Focus Areas
TSK-001 | Jean | Fix Remo robot face (human → original) for Level 4 Month 1 Lesson 10; update lesson-references + SKILLS.md | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | remoed-lesson-creation skill · ~9:12 PM
TSK-002 | Jean | Forgot/reset password: set new password immediately instead of emailing temporary password (all user types) | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | Password reset UX shortened · ~9:12 PM
TSK-003 | Jean | Profile validation: valid email only; inline field errors; remove redundant country; block save without required fields | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | Student/profile form validation · ~9:22 PM
TSK-004 | Jean | Phone: phone number only (not national number); parent/guardian = emergency contact | Phase 1 (Sep 26–27) | Done | Medium | 2026-09-26 | 2026-09-26 | Contact fields aligned · ~9:30 PM
TSK-005 | Jean | Password requirements below field + strength meter (weak / strong / super strong) | Phase 1 (Sep 26–27) | Done | Medium | 2026-09-26 | 2026-09-26 | Change-password / reset UI · ~10:06 PM
TSK-006 | Jean | Lucide eye/eye-off on all password fields (no emoji); fix change-password bugs to succeed | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | password-toggle.js · ~10:08 PM
TSK-007 | Jean | Adopt Lucide.dev as system icon reference; document in SKILLS.md + STABLE_BASELINE.md | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | lucide-icons.js catalog · ~10:15 PM
TSK-008 | Jean | Widen password UI for desktop; eye toggle inside field; require symbol in password rules | Phase 1 (Sep 26–27) | Done | Medium | 2026-09-26 | 2026-09-26 | Desktop layout polish · ~10:22 PM
TSK-009 | Jean | Restore student waiting room when teacher not in live classroom yet (mini-game/video); Lucide icons for camera etc. | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | student-class-wait.js · ~10:25 PM
TSK-010 | Jean | Teacher guide Skip; careful chat bad-word filter (student sees ****; teacher can reveal); Lucide mic/cam controls | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | Live classroom chat + media pills · ~10:51 PM
TSK-011 | Jean | Hide Give Feedback after submit; QA issue → notify students to reschedule; bi-monthly cut-offs; payslip withdrawable amount | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-27 | Feedback + QA notify + payroll periods · ~11:46 PM
TSK-012 | Jean | Student booking cap: max 2 classes / 1 hour per student local day | Phase 1 (Sep 26–27) | Done | High | 2026-09-26 | 2026-09-26 | DAILY_CLASS_LIMIT · ~11:57 PM
TSK-013 | Jean | Teaching Fee wallet UX: Total Earnings header; Available to Withdraw; after withdraw keep cut-off amount + label Withdrawn (not ₱0) | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | teacher-service-fee.html iterations · ~12:04–12:17 AM
TSK-014 | Jean | Payslip status still Pending after withdraw → show withdrawn/completed correctly | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | Payslip lifecycle mapping · ~12:21 AM
TSK-015 | Jean | Remove redundant Withdrawn chip beside Pending Earnings | Phase 1 (Sep 26–27) | Done | Medium | 2026-09-27 | 2026-09-27 | Teaching Fee wallet cleanup · ~12:26 AM
TSK-016 | Jean | Payslip amount bug: showed PHP 1000 instead of 1140 (include class fee / max snap vs live) | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | Payslip totals fix · ~12:27 AM
TSK-017 | Jean | Undo salary dispense for current cut-off so amounts can be retested | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | scripts/undo-cutoff-salary-dispense.js · ~12:30 AM
TSK-018 | Jean | MariBank max daily withdraw PHP 50,000 note when Available exceeds limit | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | Teaching Fee + withdraw modal · ~12:45 AM
TSK-019 | Jean | Min withdraw PHP 100 (else rolls to next cut-off); unwithdrawn DISBURSED carries forward; daily max PHP 50k | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | payrollWithdrawService + dispense carry-forward · ~12:53 AM
TSK-020 | Jean | Post-assessment Plans: "You have taken the assessment" + Register Now; retake same email → already taken, check email | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | index.html + assessment-status API · ~1:18 AM
TSK-021 | Jean | Register: first+last name then email; prefill email from assessment link; fix Invalid/already used trial link — no expire except email already registered | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | student-register.html + auth trial resolve · ~1:38 AM
TSK-022 | Jean | Credit expiry: keep longest plan expiry; buying a shorter plan must not shorten remaining days (add/stack correctly) | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | creditExpiry / plan stacking · ~1:53–1:54 AM
TSK-023 | Jean | Per-plan FIFO credit lots: earlier subscription credits expire/use first before newer plan credits (e.g. 3mo then 6mo) | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | creditLots + bookingCreditLedger · ~2:03 AM
TSK-024 | Jean | Book Class: Booking Details must be centered modal (not side panel); block jump-forward lessons; allow back/reschedule | Phase 1 (Sep 26–27) | Done | High | 2026-09-27 | 2026-09-27 | student-book modal + studentLessonUnlock + journey · ~2:14 AM
TSK-025 | Jean | Generate Excel prompts/fixes tracker (Done vs Pending) from Sep 26 9PM PHT → now, matching Pre-Launch tracker layout | Phase 1 (Sep 26–27) | Done | Medium | 2026-09-27 | 2026-09-27 | docs/RemoEdPH-Prompts-Fixes-Tracker-2026-09-26-9PM.xlsx · ~2:28 AM
Legend: | Done | Ongoing | Scheduled | Pending
Generated: | 2026-09-27 02:29 PHT
Source: | Cursor agent transcript prompts from Sep 26 9:00 PM PHT onward (meta/briefly-inform prompts omitted).

## Raw Prompt Log
# | Timestamp (UTC+8) | User Prompt (summary) | Status
1 | 2026-09-26 21:12 | Why Remo the robot's face become a human? Change it to its original face for L4M1 Lesson 10… | Done
2 | 2026-09-26 21:12 | First-time forgot/reset password → change password immediately (no temp email password) | Done
3 | 2026-09-26 21:22 | Valid email only; inline validation errors; no redundant country; required fields to save | Done
4 | 2026-09-26 21:30 | Only phone number not national number; parent/guardian = emergency contact | Done
5 | 2026-09-26 22:06 | Password requirements below field + weak/strong/super strong meter | Done
6 | 2026-09-26 22:08 | Eye icon all password fields; no emoji; fix change-password to succeed | Done
7 | 2026-09-26 22:15 | Use lucide.dev icons; save to SKILLS.md + STABLE_BASELINE.md | Done
8 | 2026-09-26 22:22 | Widen desktop password UI; eye in field; include symbol in password rules | Done
9 | 2026-09-26 22:25 | Restore student waiting room if teacher not in class; Lucide system icons | Done
10 | 2026-09-26 22:51 | Teacher guide Skip; careful chat bad-word filter; Lucide mic/cam icons | Done
11 | 2026-09-26 23:46 | Feedback still shows after submit; QA reschedule notify; bi-monthly cut-offs + payslip withdrawable | Done
12 | 2026-09-26 23:57 | Students max 2 classes / 1 hour per day when booking | Done
13 | 2026-09-27 00:04 | Teacher already withdraw → show 0.00 again (later superseded by keep-amount rule) | Done
14 | 2026-09-27 00:07 | Show Available to Withdraw (photo) | Done
15 | 2026-09-27 00:11 | Total Earnings header; Available to Withdraw instead of Payment Summary / net payable | Done
16 | 2026-09-27 00:17 | Keep amount after withdraw; label → Withdrawn (not zero) | Done
17 | 2026-09-27 00:21 | Payslip still Pending after withdraw | Done
18 | 2026-09-27 00:26 | Remove redundant Withdrawn beside Pending Earnings | Done
19 | 2026-09-27 00:27 | Payslip shows 1000 instead of 1140 | Done
20 | 2026-09-27 00:30 | Undo salaries dispensed this cut-off for retest | Done
21 | 2026-09-27 00:45 | MariBank max daily withdraw PHP 50,000 note if exceed | Done
22 | 2026-09-27 00:53 | Min withdraw PHP 100 / rollover to next cut-off / unwithdrawn carries / PHP 50k daily max | Done
23 | 2026-09-27 01:18 | Post-assessment Plans: Register Now; retake email → already taken, check email | Done
24 | 2026-09-27 01:38 | Register first+last name then email; prefill from email link; no trial expire except email registered | Done
25 | 2026-09-27 01:43 | Generate Excel of prompts/bugs fixed or pending (first request) | Done
26 | 2026-09-27 01:53 | Credit expiry should follow longest plan expiry even after buying a shorter plan | Done
27 | 2026-09-27 01:54 | Clarify: longest expiry still applies OR days left should add up | Done
28 | 2026-09-27 02:03 | FIFO per-plan lots: earlier plan credits expire/use first before newer plan credits | Done
29 | 2026-09-27 02:14 | Booking Details should not be on the side; no jump-forward lessons; allow back/reschedule | Done
30 | 2026-09-27 02:28 | Regenerate Excel prompts & fixes tracker (Sep 26 9PM → now) matching Pre-Launch layout | Done